## StitchPerfect Gantt
StitchPerfect – Digital Tailor Shop Management System
Uday Singh ¦ Roll No: 1024160031 | [5 empty] | Project Start: | 2026-08-03
Solo Developer – Frontend, System Design & Project Coordination | [5 empty] | Today: | 2026-09-16
LEGEND | Completed | In Progress
[6 empty] | Week of 03 Aug 2026 | [6 empty] | Week of 10 Aug 2026 | [6 empty] | Week of 17 Aug 2026 | [6 empty] | Week of 24 Aug 2026 | [6 empty] | Week of 31 Aug 2026 | [6 empty] | Week of 07 Sep 2026
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | 3 M | 4 T | 5 W | 6 T | 7 F | 8 S | 9 S | 10 M | 11 T | 12 W | 13 T | 14 F | 15 S | 16 S | 17 M | 18 T | 19 W | 20 T | 21 F | 22 S | 23 S | 24 M | 25 T | 26 W | 27 T | 28 F | 29 S | 30 S | 31 M | 1 T | 2 W | 3 T | 4 F | 5 S | 6 S | 7 M | 8 T | 9 W | 10 T | 11 F | 12 S | 13 S
Week 1: Project Ideation & Problem Identification
Problem analysis & project ideation | Uday Singh | 100% | 2026-08-03 | 2026-08-09
Identify traditional tailor shop challenges | Uday Singh | 100% | 2026-08-03 | 2026-08-09
Define users & objectives of StitchPerfect | Uday Singh | 100% | 2026-08-03 | 2026-08-09
Week 2: Requirement Analysis & System Planning
Define functional requirements & modules | Uday Singh | 100% | 2026-08-10 | 2026-08-16
Plan order, measurement & worker workflows | Uday Singh | 100% | 2026-08-10 | 2026-08-16
Plan system architecture & database structure | Uday Singh | 100% | 2026-08-10 | 2026-08-16
Week 3: UI/UX Design & Frontend Planning
Design navigation flow & user interfaces | Uday Singh | 100% | 2026-08-17 | 2026-08-23
Plan Admin Panel & Worker Console | Uday Singh | 100% | 2026-08-17 | 2026-08-23
Create reusable responsive UI component plan | Uday Singh | 100% | 2026-08-17 | 2026-08-23
Week 4: Frontend Development
Develop main pages & navigation | Uday Singh | 100% | 2026-08-24 | 2026-08-30
Build customer and order interfaces | Uday Singh | 100% | 2026-08-24 | 2026-08-30
Create initial Admin Panel & Worker Console | Uday Singh | 100% | 2026-08-24 | 2026-08-30
Implement responsive layouts | Uday Singh | 100% | 2026-08-24 | 2026-08-30
Week 5: Frontend Modules & System Diagrams
Complete major frontend modules | Uday Singh | 100% | 2026-08-31 | 2026-09-06
Develop delivery & ready-product interfaces | Uday Singh | 100% | 2026-08-31 | 2026-09-06
Prepare Level-0, Level-1 & Level-3 DFDs | Uday Singh | 100% | 2026-08-31 | 2026-09-06
Refine navigation, forms & user experience | Uday Singh | 100% | 2026-08-31 | 2026-09-06
Week 6: Frontend Completion & Backend Planning
Finalize frontend interfaces & workflows | Uday Singh | 50% | 2026-09-07 | 2026-09-13
Review frontend and identify integration areas | Uday Singh | 50% | 2026-09-07 | 2026-09-13